InterviewForge AI

Task Division & Execution Tracker — 8 Weeks, 3-Member Team

This is a live tracker, not a plan document. Update the Status column weekly as work progresses.

# Team & Domain Ownership

| Member | Primary Domain |
| --- | --- |
| Krishna (Frontend) | Frontend — all UI screens, client-side logic, responsive/accessible layout |
| Akhilesh (Backend & DB) | Backend & Database — API, auth, Prisma schema, deployment/DevOps |
| Ayush (AI Integration) | AI Integration — Gemini prompts, resume parsing, evaluation & report generation logic |

# Weekly Task Tracker

| Week | Task | Owner | Status |
| --- | --- | --- | --- |
| 1 | Wireframe core screens (login, dashboard, resume upload, interview, report, history) | Krishna (Frontend) | To Do |
|  | Design DB schema / ERD (Users, Resumes, Interviews, Questions, Responses, Reports) | Akhilesh (Backend & DB) | To Do |
|  | Set up GitHub repo, branching strategy, project board | All 3 | To Do |
|  | Create free-tier accounts: Vercel, Render, Supabase | Akhilesh (Backend & DB) | To Do |
|  | Create Gemini API key (Google AI Studio) | Ayush (AI Integration) | To Do |
| 2 | Express project structure + Prisma migrations | Akhilesh (Backend & DB) | To Do |
|  | Register/login/refresh/logout endpoints (JWT) | Akhilesh (Backend & DB) | To Do |
|  | Role-based access middleware | Akhilesh (Backend & DB) | To Do |
|  | Login & Signup screens (Next.js + Tailwind) | Krishna (Frontend) | To Do |
|  | Wire Login/Signup UI to real auth API | Krishna (Frontend) | To Do |
|  | Deploy staging backend (Render) + staging frontend (Vercel) | Akhilesh (Backend & DB) | To Do |
| 3 | Interviews / Questions / Responses tables & endpoints | Akhilesh (Backend & DB) | To Do |
|  | Interview Setup screen (category → role → mode → start) | Krishna (Frontend) | To Do |
|  | Live Interview screen (question card, timer, text input, progress bar) | Krishna (Frontend) | To Do |
|  | Placeholder-question session flow end-to-end | Krishna (Frontend) | To Do |
|  | Define API contract for question/response payloads (shared with AI module) | Akhilesh (Backend & DB) | To Do |
| 4 | Build isolated AI Service module (generateQuestions, evaluateResponse, generateReport) | Ayush (AI Integration) | To Do |
|  | Gemini integration — Technical + HR question generation | Ayush (AI Integration) | To Do |
|  | Gemini integration — response scoring | Ayush (AI Integration) | To Do |
|  | JSON-schema validation of AI responses before backend trusts them | Ayush (AI Integration) | To Do |
|  | Replace placeholder questions in Live Interview screen with real AI output | Krishna (Frontend) | To Do |
|  | Backend endpoint to call AI Service and store results | Akhilesh (Backend & DB) | To Do |
| 5 | Resume upload to Supabase Storage (PDF/DOCX) | Akhilesh (Backend & DB) | To Do |
|  | AI resume-parsing prompt → structured JSON output | Ayush (AI Integration) | To Do |
|  | Resume review/edit screen for the student | Krishna (Frontend) | To Do |
|  | Wire parsed resume data into question-generation prompt | Ayush (AI Integration) | To Do |
| 6 | Report generation logic on session completion | Ayush (AI Integration) | To Do |
|  | Results/Report screen with question-by-question feedback | Krishna (Frontend) | To Do |
|  | History + score-trend view (Recharts) | Krishna (Frontend) | To Do |
|  | Backend endpoints for report/history data | Akhilesh (Backend & DB) | To Do |
|  | Stretch: Web Speech API integration for voice input | Krishna (Frontend) | To Do |
| 7 | Structured test pass: empty resume, AI timeout, abandoned session, slow network | All 3 | To Do |
|  | Cross-browser + mobile breakpoint check | Krishna (Frontend) | To Do |
|  | Fix defects found in testing | All 3 | To Do |
|  | UI/spacing/loading-state polish | Krishna (Frontend) | To Do |
|  | Finish/stabilize voice mode or confirm text-mode fallback | Ayush (AI Integration) | To Do |
| 8 | Finalize production deployment (Vercel + Render + Supabase) | Akhilesh (Backend & DB) | To Do |
|  | Set production environment variables/secrets | Akhilesh (Backend & DB) | To Do |
|  | Write final README + API notes | Akhilesh (Backend & DB) | To Do |
|  | Write individual contribution summary | All 3 | To Do |
|  | Prepare and rehearse demo script | All 3 | To Do |
|  | Record fallback demo video | Krishna (Frontend) | To Do |

# Shared / Dependent Task Review

Some tasks touch more than one member's domain. These require a review from all 3 before merging into main:

- API contracts (request/response shape between Frontend, Backend, and AI Service) — changed only after a quick 3-way check so no one builds against a stale shape

- Database schema changes — Backend proposes, all 3 confirm before running a migration, since Frontend and AI modules both depend on field names/types

- AI response JSON schema — AI Integration proposes, Backend confirms it can validate/store it, Frontend confirms it can render it

- Any change to an already-merged shared file (e.g., shared types/interfaces) — flagged in the team channel before pushing

Rule of thumb: if a change only affects your own domain folder, merge directly. If it changes something another member's code calls or depends on, get a quick sign-off first — a short message is enough, no formal review process needed for a 3-person team.